## Gap Matrix
ID | Volume | Area | Issue | Severity | Likelihood | Recommendation | Priority | Owner | Status | Cross-Refs
GAP-ARCH-001 | Vol 01 Architecture | Plugin SDK | Plugin SDK contract for third-party authors not yet published | HIGH | HIGH | Publish SDK with base classes + manifest schema + CI lint; ship by MVP | P1 | Platform Eng | Open | Vol 01 §4.2
GAP-ARCH-002 | Vol 01 Architecture | Event Bus | ADR-001 RabbitMQ vs Kafka not decided | HIGH | MED | Decision pending; default Kafka (MSK) — confirm before MVP | P1 | Architecture | Open | Vol 01 §17
GAP-ARCH-003 | Vol 01 Architecture | Search | ADR-002 OpenSearch vs Algolia | HIGH | MED | Default OpenSearch self-hosted; confirm pre-MVP | P1 | Architecture | Open | Vol 01 §17
GAP-ARCH-004 | Vol 01 Architecture | AI Store | ADR-003 Qdrant vs pgvector | MED | MED | Default Qdrant; finalize Phase 3 | P2 | AI Architecture | Open | Vol 01 §17
GAP-ARCH-005 | Vol 01 Architecture | DB | Aurora MySQL vs PostgreSQL | HIGH | LOW | Aurora MySQL for WP native; revisit at Phase 4 | P1 | Architecture | Resolved | Vol 01 §17
GAP-ARCH-006 | Vol 01 Architecture | Multi-tenancy | Tenant migration between modes (pooled→silo) | MED | MED | Design migration runbook; staged with downtime window | P2 | SRE | Open | Vol 01 §9.1
GAP-ARCH-007 | Vol 01 Architecture | Resilience | Outbox relay implementation language | MED | LOW | Go binary preferred over PHP CLI; resolve ADR-006 | P2 | Platform Eng | Open | Vol 01 §17
GAP-PRD-001 | Vol 02 PRD | Pricing | Final commission tier numbers not finalized | HIGH | HIGH | Finance + product confirm $99/499/1999 + Enterprise custom | P1 | CPO + Finance | Open | Vol 02 §6.1
GAP-PRD-002 | Vol 02 PRD | AI quotas | Per-tier AI completion limits not load-tested | MED | HIGH | Run cost projection for top-50 anticipated tenants | P2 | PM + Finance | Open | Vol 02 §6.1
GAP-PRD-003 | Vol 02 PRD | I18n | Phase-1 launch locales not chosen | MED | MED | Pick 5 launch locales: en, fr, de, es, pt-BR | P2 | CPO | Open | Vol 02 §5.9
GAP-PRD-004 | Vol 02 PRD | Vendor onboarding | Time-to-first-sale metric instrumentation missing | MED | HIGH | Instrument event chain | P2 | Data | Open | Vol 02 §8
GAP-PRD-005 | Vol 02 PRD | Buyer AI | Conversational discovery scope deferred but UX unclear | LOW | MED | Defer to Phase 3; clarify expected behavior | P3 | PM | Open | Vol 02 EPIC-17
GAP-BRD-001 | Vol 03 BRD | Tax | US Marketplace Facilitator state map needs finalization | HIGH | HIGH | Legal review per state; ship in MVP for top-10 GMV states | P1 | Compliance + Legal | Open | Vol 03 §8.4
GAP-BRD-002 | Vol 03 BRD | Vendor Agreement | Per-jurisdiction template missing | HIGH | HIGH | Engage local counsel for US/EU/UK/CA | P1 | Legal | Open | Vol 03 §10
GAP-BRD-003 | Vol 03 BRD | SLA | Service-credit policy precise wording | MED | MED | Legal draft; CSM sign-off | P2 | Legal + CSM | Open | Vol 03 §7
GAP-BRD-004 | Vol 03 BRD | Prohibited | Category list per region needs regulator review | HIGH | MED | Compliance + Legal per region; final by Phase 2 | P2 | Compliance | Open | Vol 03 §5.14.2
GAP-BRD-005 | Vol 03 BRD | Resellers | Reseller-sub-tenant contract template | LOW | LOW | Phase 4 work | P4 | Legal | Open | Vol 03 §5.13
GAP-FSD-001 | Vol 04 FSD | Dispute escalation | Terminal states for cross-jurisdictional disputes ambiguous | MED | MED | Add dispute_jurisdiction column; spec terminal state set | P2 | PM + Eng | Open | Vol 04 §11
GAP-FSD-002 | Vol 04 FSD | KYC retry | KYC provider webhook retry policy not defined | MED | MED | Implement inbox pattern with 5 retries / 30min backoff | P2 | Eng | Open | Vol 04 §18
GAP-FSD-003 | Vol 04 FSD | Multi-currency | Cross-currency commission reversal precision | HIGH | MED | Persist FX captured at order; reversal uses same rate | P1 | Eng | Resolved | Vol 04 §8
GAP-FSD-004 | Vol 04 FSD | Order snapshot | Snapshot retention vs PII erasure conflict | HIGH | MED | Snapshot retains pseudonymized buyer; legal retention applies | P1 | DPO + Eng | Open | Vol 04 §7
GAP-SRS-001 | Vol 05 SRS | NFR P-006 | Sustained 5k/min order ingestion not yet measured | HIGH | MED | Build k6 scenario; run at staging | P1 | SRE | Open | Vol 05 §5.1
GAP-SRS-002 | Vol 05 SRS | NFR Sec | Annual pentest scope not contracted | MED | MED | Engage CREST-accredited firm | P2 | Security | Open | Vol 05 §5.4
GAP-SRS-003 | Vol 05 SRS | NFR DR | Tier-0 RPO 5min not validated by snapshot drill | HIGH | MED | Monthly DR drill scheduled | P1 | SRE | Open | Vol 05 §5.3
GAP-DB-001 | Vol 06 DB | Partitioning | Monthly partition maintenance job not yet scripted | HIGH | HIGH | Cron job in mercato-core to add next-month partition on day 15 | P1 | DB Architect | Open | Vol 06 §5
GAP-DB-002 | Vol 06 DB | RLS | Pooled-mode trigger overhead unmeasured | MED | HIGH | Benchmark; expect ~3% latency hit | P2 | DB Architect | Open | Vol 06 §6
GAP-DB-003 | Vol 06 DB | Append-only | DB role grant audit not implemented | MED | MED | Migration that enforces grants; CI verify | P2 | Security + DB | Open | Vol 06 §7
GAP-DB-004 | Vol 06 DB | Migration | Online schema change tool selection (gh-ost vs pt-online) | LOW | LOW | gh-ost default; pt-online for cases gh-ost can't | P3 | SRE | Open | Vol 06 §8
GAP-API-001 | Vol 07 OpenAPI | Webhooks | Tenant outbound webhook signature spec | MED | MED | HMAC SHA256, header X-Mercato-Signature, replay window 5min | P2 | API | Resolved | Vol 04 §13
GAP-API-002 | Vol 07 OpenAPI | Rate limit | Per-endpoint rate-limit table not in spec | MED | MED | Add to OpenAPI extensions x-rate-limit | P2 | API | Open | Vol 09 §13.4
GAP-API-003 | Vol 07 OpenAPI | Versioning | v2 deprecation timeline policy | LOW | LOW | 2-minor deprecation per SemVer | P3 | API | Resolved | Vol 01 §4.5
GAP-UX-001 | Vol 08 UX | Mobile | Native mobile app deferred — mobile web SPA optimization | HIGH | HIGH | Optimize SPAs for mobile web in Phase 1; native app Phase 4 | P2 | UX + Eng | Open | Vol 08 §3.7
GAP-UX-002 | Vol 08 UX | Design tokens | Tenant token JSON schema not published | MED | MED | Publish JSON Schema, validate on save | P2 | UX + Eng | Open | Vol 01 §12
GAP-UX-003 | Vol 08 UX | SSO UX | Enterprise SSO config flow not designed | HIGH | MED | Design wizard; Phase 3 | P2 | UX | Open | Vol 04 §22
GAP-UX-004 | Vol 08 UX | Microcopy | Comprehensive microcopy library | MED | MED | Build microcopy in 5 launch locales | P2 | UX Writer | Open | Vol 08 §3.9
GAP-SEC-001 | Vol 09 Security | BYOK | Tenant BYOK UX + key validation | MED | LOW | Phase 4 — design BYOK workflow + grant management | P3 | Security | Open | Vol 09 §6.3
GAP-SEC-002 | Vol 09 Security | DSAR | Identity verification for DSAR not finalized | HIGH | MED | Two-factor identity (account + email + SMS code) | P1 | DPO | Open | Vol 09 §10.2
GAP-SEC-003 | Vol 09 Security | WebAuthn | WebAuthn rollout for vendors | MED | MED | Phase 2 — implement via existing libs | P2 | Security | Open | Vol 09 §4.1
GAP-SEC-004 | Vol 09 Security | SIEM | SIEM choice not finalized | MED | MED | Datadog Security default; Wazuh self-hosted for cost-sensitive | P2 | Security + SRE | Open | Vol 09 §8.2
GAP-SEC-005 | Vol 09 Security | CSP | CSP nonces require build-time SPA changes | MED | MED | Implement nonce injection in SSR layer | P2 | Web Eng | Open | Vol 09 §13.6
GAP-QA-001 | Vol 10 QA | E2E | Top-30 Playwright scenarios authoring in progress | HIGH | HIGH | Author 30; ship by MVP gate | P1 | QA | Open | Vol 10 §6
GAP-QA-002 | Vol 10 QA | Perf | k6 scripts for NFR-P set | HIGH | HIGH | Author; integrate with nightly | P1 | SRE + QA | Open | Vol 10 §7
GAP-QA-003 | Vol 10 QA | Visual | Percy / Chromatic vendor choice | LOW | LOW | Percy default; cost-compare quarterly | P3 | QA | Open | Vol 10 §3.1
GAP-QA-004 | Vol 10 QA | UAT | BugHerd vs Marker.io vs Sentry Session Replay | LOW | LOW | Marker.io default for UAT | P3 | QA + UX | Open | Vol 10 §10.1
GAP-QA-005 | Vol 10 QA | Chaos | Litmus or Chaos Mesh | MED | LOW | Litmus default; quarterly cadence | P2 | SRE | Open | Vol 10 §8
GAP-DEV-001 | Vol 11 DevOps | DR Drill | Quarterly DR drill ops cadence | HIGH | HIGH | Schedule; first drill within 30d of MVP launch | P1 | SRE | Open | Vol 11 §9.2
GAP-DEV-002 | Vol 11 DevOps | Multi-region | Active/passive failover not validated | HIGH | MED | Annual full dry-run | P1 | SRE | Open | Vol 11 §9.3
GAP-DEV-003 | Vol 11 DevOps | Cost model | Per-tenant cost attribution in CUR | MED | MED | Tag everything tenant_id; nightly ETL | P2 | FinOps | Open | Vol 11 §10.4
GAP-DEV-004 | Vol 11 DevOps | Service mesh | Linkerd vs Istio vs Cilium | MED | LOW | Linkerd default for lower complexity | P2 | SRE | Open | Vol 01 §17
GAP-DEV-005 | Vol 11 DevOps | Argo Rollouts | Canary thresholds not yet validated | MED | MED | 5/25/50/100 with 5min soak; SLO-aware analysis | P2 | SRE | Open | Vol 11 §7.4
GAP-AI-001 | Vol 12 AI | Vector store | Qdrant prod deployment patterns | MED | MED | Run on EKS with 3-node cluster; snapshot to S3 | P2 | AI Eng | Open | Vol 12 §13
GAP-AI-002 | Vol 12 AI | Eval set | Per-feature golden sets to be authored | HIGH | HIGH | 200 examples per feature; hand-graded | P1 | AI + PM | Open | Vol 12 §8.1
GAP-AI-003 | Vol 12 AI | BYOM | Enterprise BYOM contract clauses | LOW | LOW | Phase 4 | P4 | Legal + AI | Open | Vol 12 §12
GAP-AI-004 | Vol 12 AI | Provider | Provider zero-retention contracts for OpenAI/Anthropic | HIGH | MED | Procure Enterprise tier with zero retention | P1 | Procurement | Open | Vol 12 §14.1
GAP-AI-005 | Vol 12 AI | PII redaction | Presidio false positive rate | MED | MED | Tune for vendor product copy; custom recognizers | P2 | AI Eng | Open | Vol 12 §5.1
GAP-X-001 | Cross | Migration | Dokan/WCFM importer end-to-end test | MED | MED | Phase 4 importer; dry-run + 24h rollback | P3 | Eng | Open | Vol 04 §23
GAP-X-002 | Cross | Localization | Per-locale legal text reviewed by counsel | HIGH | MED | Pre-Phase 2 | P2 | Legal | Open | Vol 03 §8
GAP-X-003 | Cross | Observability | Tenant-aware Grafana dashboards | HIGH | HIGH | Tagging discipline + per-tenant variable | P1 | SRE | Open | Vol 11 §8
GAP-X-004 | Cross | Status page | Status page tooling | MED | LOW | StatusPage.io default | P2 | SRE | Open | Vol 03 §7
GAP-X-005 | Cross | Compliance | SOC-2 Type II first audit | HIGH | MED | 12-month observation; engage auditor at month 1 | P2 | Compliance | Open | Vol 09 §15

## Summary by Volume
Volume | Total Gaps | Critical | High | Med | Low | Open | Resolved
Cross | 5 | 0 | 3 | 2 | 0 | 5 | 0
Vol 01 Architecture | 7 | 0 | 4 | 3 | 0 | 6 | 1
Vol 02 PRD | 5 | 0 | 1 | 3 | 1 | 5 | 0
Vol 03 BRD | 5 | 0 | 3 | 1 | 1 | 5 | 0
Vol 04 FSD | 4 | 0 | 2 | 2 | 0 | 3 | 1
Vol 05 SRS | 3 | 0 | 2 | 1 | 0 | 3 | 0
Vol 06 DB | 4 | 0 | 1 | 2 | 1 | 4 | 0
Vol 07 OpenAPI | 3 | 0 | 0 | 2 | 1 | 1 | 2
Vol 08 UX | 4 | 0 | 2 | 2 | 0 | 4 | 0
Vol 09 Security | 5 | 0 | 1 | 4 | 0 | 5 | 0
Vol 10 QA | 5 | 0 | 2 | 1 | 2 | 5 | 0
Vol 11 DevOps | 5 | 0 | 2 | 3 | 0 | 5 | 0
Vol 12 AI | 5 | 0 | 2 | 2 | 1 | 5 | 0

## Severity Heatmap
Severity \ Priority | P1 | P2 | P3 | P4
CRITICAL | 0 | 0 | 0 | 0
HIGH | 20 | 5 | 0 | 0
MED | 0 | 26 | 2 | 0
LOW | 0 | 0 | 5 | 2

## Legend
Field | Meaning
Severity | CRITICAL/HIGH/MED/LOW — impact if unresolved
Likelihood | HIGH/MED/LOW — probability the issue materializes
Priority | P1 = block MVP, P2 = block Phase 2, P3 = Phase 3+, P4 = backlog
Status | Open / In Progress / Resolved / Deferred
Cross-Refs | Volume sections that touch this gap