## Backlog
Epic | Feature | Story ID | User Story | Acceptance Criteria | Dependencies | Plugin | FR Refs | Phase | Estimate (pts) | Status | Priority
EP-01 Core Framework | Plugin Manifest | US-CORE-001 | As a plugin developer, I declare my plugin via plugin.json | - Manifest schema validates - Cycle detected → refusal - Topological boot order | - | mercato-core | FR-CORE-001..003 | P1 MVP | 8 | Ready | P1
EP-01 Core Framework | Outbox | US-CORE-002 | As a domain developer, I emit events via outbox | - DB tx wraps insert - Relay daemon publishes - DLQ at retries=6 | - | mercato-core | FR-CORE-004 | P1 MVP | 13 | Ready | P1
EP-01 Core Framework | RBAC | US-CORE-003 | Capability check API | - mercato_user_can() signature - Resource ownership *_own - Cache 60s | - | mercato-core | FR-CORE-006..007 | P1 MVP | 8 | Ready | P1
EP-01 Core Framework | Capability JWT | US-CORE-004 | Tenant JWT refresh | - 24h TTL - JWKS rotation - Revocation list polled | Control Plane | mercato-core, mercato-enterprise | FR-ENT-001..002 | P1 MVP | 8 | Ready | P1
EP-01 Core Framework | Migrator | US-CORE-005 | DB migration runner | - up/down/verify - CI dry-run | - | mercato-core | FR-CORE-005 | P1 MVP | 5 | Ready | P1
EP-01 Core Framework | Idempotency | US-CORE-006 | Idempotency-Key handling | - Replay returns original - 24h TTL - scoped tenant+user+endpoint | - | mercato-core | FR-CORE-009 | P1 MVP | 5 | Ready | P1
EP-01 Core Framework | Hook adapter | US-CORE-007 | WC hook adapter | - map per Vol 04 §3.6 - versioned in one file | WC HPOS | mercato-core | FR-CORE-001 | P1 MVP | 5 | Ready | P1
EP-02 Vendor Lifecycle | Registration | US-VEN-001 | Vendor public sign-up form | - Validation - Event emitted - Confirmation email | Core | mercato-vendors | FR-VEN-001..003 | P1 MVP | 8 | Ready | P1
EP-02 Vendor Lifecycle | KYC | US-VEN-002 | Stripe Identity onboarding | - Hosted URL - Webhook updates status - Vendor banner | Core, Stripe | mercato-vendors, mercato-kyc-kyb, mercato-stripe-connect | FR-VEN-004..006, FR-KYC-001..003 | P1 MVP | 13 | Ready | P1
EP-02 Vendor Lifecycle | Approval | US-VEN-003 | Tenant admin approve/reject/suspend | - Reason captured - Audit - Vendor notified | Core | mercato-vendors | FR-VEN-005..007 | P1 MVP | 8 | Ready | P1
EP-02 Vendor Lifecycle | Storefront settings | US-VEN-004 | Vendor configures storefront | - Slug uniqueness - Brand fields - Return policy | Core | mercato-vendors | FR-VEN-001 | P1 MVP | 8 | Ready | P1
EP-02 Vendor Lifecycle | Staff roles | US-VEN-005 | Vendor invites staff | - 6 roles - Cap to inviter perms - Audit | Core RBAC | mercato-vendors | FR-VEN-010 | P2 | 8 | Backlog | P2
EP-02 Vendor Lifecycle | Data export | US-VEN-006 | Vendor downloads data export | - Signed S3 URL 7d - Async job - Includes all entities | Core, S3 | mercato-vendors | FR-VEN-008 | P2 | 8 | Backlog | P2
EP-02 Vendor Lifecycle | Closure | US-VEN-007 | Vendor closes store | - Block if obligations open - 30d anonymize - Legal hold support | Core, Compliance | mercato-vendors | FR-VEN-009 | P3 | 5 | Backlog | P3
EP-03 Catalog | Product CRUD | US-PROD-001 | Vendor creates product via SPA | - 422 on missing fields - Event emitted - Shadow projected | Vendors | mercato-products | FR-PROD-001..002 | P1 MVP | 13 | Ready | P1
EP-03 Catalog | Bulk import | US-PROD-002 | CSV import 10k rows | - Validation - Error report - Async job | Core, S3 | mercato-products | FR-PROD-005 | P2 | 13 | Backlog | P2
EP-03 Catalog | Inline edit | US-PROD-003 | Edit price/stock without form | - Field-level PATCH - Optimistic concurrency | Core | mercato-products | FR-PROD-002 | P2 | 5 | Backlog | P2
EP-03 Catalog | Variations | US-PROD-004 | Variable products up to 250 | - Attribute matrix - Per-variation SKU | Core | mercato-products | FR-PROD-004 | P2 | 13 | Backlog | P2
EP-03 Catalog | Archive | US-PROD-005 | Soft-delete product | - 30d archive - Snapshot preserved | Core | mercato-products | FR-PROD-003 | P1 MVP | 5 | Ready | P1
EP-03 Catalog | Moderation | US-PROD-006 | Tenant moderation mode | - 3 modes - AI assist | Core | mercato-products, mercato-ai-copilot | FR-PROD-007 | P2 | 13 | Backlog | P2
EP-03 Catalog | Browse | US-PROD-007 | Faceted catalog browse | - Filters - Pagination - Sort | Search | mercato-products, mercato-search | FR-PROD-007..008 | P2 | 13 | Backlog | P2
EP-03 Catalog | PDP | US-PROD-008 | PDP shows vendor + ratings + ship-to | - Vendor identity - Ratings - Ship eligibility | Core | mercato-products | FR-PROD-008 | P1 MVP | 8 | Ready | P1
EP-04 Orders | Split cart | US-ORD-001 | Multi-vendor checkout splits | - 1 parent + N sub-orders - Shipping per vendor - Idempotent | Products, Vendors, WC HPOS | mercato-orders | FR-ORD-001..002 | P1 MVP | 21 | Ready | P1
EP-04 Orders | Per-vendor shipping | US-ORD-002 | Shipping rates per vendor | - Zone matrix - Cart display | Vendors | mercato-orders | FR-ORD-002 | P1 MVP | 13 | Ready | P1
EP-04 Orders | Vendor scope | US-ORD-003 | Vendor sees only own | - 404 cross-vendor | Core RBAC | mercato-orders | FR-ORD-004 | P1 MVP | 5 | Ready | P1
EP-04 Orders | Fulfillment | US-ORD-004 | Vendor updates status + tracking | - State machine enforced - Carrier autodetect | Core | mercato-orders | FR-ORD-005..006 | P1 MVP | 8 | Ready | P1
EP-04 Orders | Buyer tracking | US-ORD-005 | Buyer consolidated tracking | - Per sub-order - Real-time | Core | mercato-orders | FR-ORD-006 | P1 MVP | 8 | Ready | P1
EP-04 Orders | Sub-cancel | US-ORD-006 | Buyer cancels sub-order | - Refund only that - Parent intact | Core | mercato-orders | FR-ORD-008 | P2 | 8 | Backlog | P2
EP-05 Commissions | Global default | US-COMM-001 | Set platform default commission | - Single rate - Effective from | Core | mercato-commissions | FR-COMM-001..002 | P1 MVP | 5 | Ready | P1
EP-05 Commissions | Overrides | US-COMM-002 | Category/vendor/product overrides | - Hierarchy resolution - Preview | Core | mercato-commissions | FR-COMM-001 | P1 MVP | 13 | Ready | P1
EP-05 Commissions | Tiered | US-COMM-003 | Tier rules by MTD GMV | - Tier resolved at order time | Core | mercato-commissions | FR-COMM-001 | P2 | 13 | Backlog | P2
EP-05 Commissions | Preview | US-COMM-004 | Preview on sample order | - Sandbox compute - No persistence | Core | mercato-commissions | FR-COMM-007 | P2 | 5 | Backlog | P2
EP-05 Commissions | Export | US-COMM-005 | Export ledger CSV/XLSX | - Date range - Per vendor | Core | mercato-commissions | FR-COMM-005 | P2 | 5 | Backlog | P2
EP-05 Commissions | Refund reversal | US-COMM-006 | Auto reversal on refund | - Append-only offset - Idempotent | Orders | mercato-commissions | FR-COMM-005..006 | P1 MVP | 13 | Ready | P1
EP-06 Payouts | Vendor balance | US-PAY-001 | Show available/pending balance | - Eligibility query - Net of holds | Commissions | mercato-payouts | FR-PAY-001 | P1 MVP | 8 | Ready | P1
EP-06 Payouts | Schedule | US-PAY-002 | Tenant configures schedule | - 4 cadences - Per-vendor opt-out | Core | mercato-payouts | FR-PAY-002 | P1 MVP | 5 | Ready | P1
EP-06 Payouts | Batch | US-PAY-003 | Trigger batch payout | - Async - Failure retry - Manual review | Stripe | mercato-payouts | FR-PAY-002..006 | P1 MVP | 13 | Ready | P1
EP-06 Payouts | Stripe Destination | US-PAY-004 | Use Destination Charges | - source_transaction set - Currency settlement | Stripe | mercato-payouts | FR-PAY-004..005 | P1 MVP | 13 | Ready | P1
EP-06 Payouts | Reconcile | US-PAY-005 | Daily ±$0.01 | - Drift alarm - Daily report | Stripe | mercato-payouts | FR-PAY-007 | P1 MVP | 13 | Ready | P1
EP-06 Payouts | Statements | US-PAY-006 | Monthly vendor statement | - PDF - Signed URL - Emailed | Notifications | mercato-payouts | FR-PAY-008 | P2 | 8 | Backlog | P2
EP-07 Reviews | Submit | US-REV-001 | Buyer leaves review | - Verified purchase - 30d window | Orders | mercato-reviews | FR-REV-001..002 | P2 | 8 | Backlog | P2
EP-07 Reviews | Vendor response | US-REV-002 | Vendor responds once | - Editable 7d | Core | mercato-reviews | FR-REV-003 | P2 | 5 | Backlog | P2
EP-07 Reviews | Moderation | US-REV-003 | Admin moderates flagged | - SLA 48h | AI moderation | mercato-reviews | FR-REV-004..005 | P2 | 8 | Backlog | P2
EP-07 Reviews | Aggregate | US-REV-004 | Aggregate rating display | - Mean + histogram - Min 10 reviews | Core | mercato-reviews | FR-REV-005..006 | P2 | 5 | Backlog | P2
EP-08 Disputes | Open | US-DIS-001 | Buyer opens dispute | - Reason + evidence - Vendor notified | Orders | mercato-disputes | FR-DIS-001..002 | P2 | 13 | Backlog | P2
EP-08 Disputes | Vendor response | US-DIS-002 | Vendor responds 72h | - Auto-escalate | Core | mercato-disputes | FR-DIS-003 | P2 | 5 | Backlog | P2
EP-08 Disputes | Admin resolve | US-DIS-003 | Tenant adjudicates | - Refund actions - Audit | Refunds | mercato-disputes | FR-DIS-004 | P2 | 13 | Backlog | P2
EP-08 Disputes | Reversal | US-DIS-004 | Refund triggers commission reversal | - Linked | Commissions | mercato-disputes | FR-DIS-006 | P2 | 5 | Backlog | P2
EP-09 Messaging | Threads | US-MSG-001 | Buyer↔Vendor threads | - Participants only - Real-time | Core | mercato-messaging | FR-MSG-001..002 | P1 MVP | 13 | Ready | P1
EP-09 Messaging | Admin moderation | US-MSG-002 | Admin read audit-logged | - Audit entry | Core RBAC | mercato-messaging | FR-MSG-005 | P2 | 5 | Backlog | P2
EP-09 Messaging | Attachments | US-MSG-003 | Image attachments | - Presign + scan | S3 | mercato-messaging | FR-MSG-004 | P2 | 8 | Backlog | P2
EP-09 Messaging | Off-platform | US-MSG-004 | Detect & flag | - Regex+AI | AI | mercato-messaging, mercato-ai-copilot | FR-MSG-003 | P3 | 13 | Backlog | P3
EP-10 Notifications | Channels | US-NOT-001 | Email/SMS/push/in-app | - Preferences | Core | mercato-notifications | FR-NOT-001 | P1 MVP | 13 | Ready | P1
EP-10 Notifications | Templates | US-NOT-002 | Per-locale templates | - Tenant override | Core | mercato-notifications | FR-NOT-002 | P2 | 8 | Backlog | P2
EP-10 Notifications | Suppression | US-NOT-003 | Bounce/complaint suppression | - Auto-applied | Sendgrid | mercato-notifications | FR-NOT-003 | P2 | 5 | Backlog | P2
EP-10 Notifications | Webhooks | US-NOT-004 | Webhook delivery | - HMAC - Retry - DLQ | Core | mercato-notifications | FR-NOT-004 | P2 | 8 | Backlog | P2
EP-11 Reports | Tenant dashboard | US-RPT-001 | GMV/take/vendors/orders | - Replica or analytics | Analytics | mercato-reports | FR-RPT-001..002 | P2 | 13 | Backlog | P2
EP-11 Reports | Vendor dashboard | US-RPT-002 | Vendor metrics | - Own data only | Analytics | mercato-reports | FR-RPT-001 | P2 | 8 | Backlog | P2
EP-11 Reports | Export | US-RPT-003 | CSV/XLSX export | - Signed URL - 24h | Core | mercato-reports | FR-RPT-004 | P2 | 5 | Backlog | P2
EP-12 Search | Query | US-SCH-001 | Sub-100ms search | - OpenSearch - Synonyms | OpenSearch | mercato-search | FR-SCH-001..002 | P2 | 13 | Backlog | P2
EP-12 Search | Filters | US-SCH-002 | Facets | - Vendor/cat/price/rating/ships-to | - | mercato-search | FR-SCH-002 | P2 | 8 | Backlog | P2
EP-12 Search | Admin config | US-SCH-003 | Synonyms + boosts | - Tenant configurable | - | mercato-search | FR-SCH-003..004 | P3 | 8 | Backlog | P3
EP-13 Subscriptions | Plan billing | US-SUB-001 | Tenant billing | - Stripe Subscription - Metered | Stripe | mercato-subscriptions | FR-SUB-001..004 | P3 | 21 | Backlog | P3
EP-13 Subscriptions | Overage | US-SUB-003 | Overage purchases | - Metered subscription items | Stripe | mercato-subscriptions | FR-SUB-004 | P3 | 8 | Backlog | P3
EP-14 Tax | Calc | US-TAX-001 | TaxJar/Avalara at checkout | - Cache 60s - Fallback zone | Engine | mercato-tax-engine | FR-TAX-001..003 | P2 | 13 | Backlog | P2
EP-14 Tax | Reports | US-TAX-002 | Vendor tax view | - Per order | Engine | mercato-tax-engine | FR-TAX-005 | P3 | 5 | Backlog | P3
EP-15 KYC | Upload | US-KYC-001 | Doc upload S3 private | - Presign - KMS - ClamAV | S3 | mercato-kyc-kyb | FR-KYC-002 | P1 MVP | 13 | Ready | P1
EP-15 KYC | Status | US-KYC-002 | Verification status | - Provider webhook | Stripe Identity | mercato-kyc-kyb | FR-KYC-003 | P1 MVP | 8 | Ready | P1
EP-15 KYC | Compliance view | US-KYC-003 | Compliance officer review | - Re-trigger | Core | mercato-kyc-kyb | FR-KYC-005 | P2 | 5 | Backlog | P2
EP-16 Fraud | Score | US-FRD-001 | Risk score per order | - Thresholds | ML | mercato-fraud-risk | FR-FRD-001..002 | P3 | 13 | Backlog | P3
EP-16 Fraud | Review | US-FRD-002 | Admin queue | - Release/refund | - | mercato-fraud-risk | FR-FRD-003 | P3 | 8 | Backlog | P3
EP-16 Fraud | Rules | US-FRD-003 | Tenant rules | - Velocity/geo/BIN | - | mercato-fraud-risk | FR-FRD-001 | P3 | 13 | Backlog | P3
EP-17 AI | Product desc | US-AI-001 | Generate desc with SSE | - Stream - Vendor accept | AI service | mercato-ai-copilot | FR-AI-001..003 | P3 | 13 | Backlog | P3
EP-17 AI | Message reply | US-AI-002 | Suggested replies | - 1–3 options | AI service | mercato-ai-copilot, mercato-messaging | FR-AI-001..003 | P3 | 13 | Backlog | P3
EP-17 AI | Moderation | US-AI-003 | Tenant moderation | - Pre/post | AI service | mercato-ai-copilot, mercato-products | FR-AI-001 | P3 | 13 | Backlog | P3
EP-17 AI | Storefront copilot | US-AI-004 | Buyer discovery | - RAG over catalog | AI service | mercato-ai-copilot | FR-AI-001 | P3 | 21 | Backlog | P3
EP-17 AI | Usage view | US-AI-005 | Tenant usage + cost | - Per vendor | Core | mercato-ai-copilot | FR-AI-004 | P3 | 8 | Backlog | P3
EP-17 AI | Transparency | US-AI-006 | AI-assisted badge | - Vendor accept | Core | mercato-ai-copilot | BR-AI-002 | P3 | 5 | Backlog | P3
EP-18 Collab | Workspaces | US-COL-001 | Vendor shared workspace | - Membership | Core | mercato-collaboration | FR-COL-001 | P4 | 13 | Backlog | P4
EP-18 Collab | Broadcast | US-COL-002 | Tenant broadcast | - Audit | Core | mercato-collaboration | FR-COL-001 | P4 | 8 | Backlog | P4
EP-19 Enterprise | Tenant provision | US-ENT-001 | Provision tenant | - 60s pooled - 5min silo | Control Plane | mercato-enterprise | FR-ENT-001 | P1 MVP | 13 | Ready | P1
EP-19 Enterprise | Branding | US-ENT-002 | Token config | - Live preview | Core | mercato-enterprise | FR-ENT-003 | P1 MVP | 8 | Ready | P1
EP-19 Enterprise | Domain | US-ENT-003 | Custom domain | - ACM - DNS validation | CP | mercato-enterprise | FR-ENT-004 | P3 | 13 | Backlog | P3
EP-19 Enterprise | Feature flags | US-ENT-004 | Runtime feature flag enforcement | - 1min latency | CP | mercato-enterprise | FR-ENT-002 | P1 MVP | 8 | Ready | P1
EP-19 Enterprise | SSO | US-ENT-005 | SAML/OIDC | - IdP metadata | CP | mercato-enterprise | FR-ENT-005 | P3 | 21 | Backlog | P3
EP-20 Migration | Dokan importer | US-MIG-001 | Import from Dokan | - Dry-run - Rollback | All | mercato-migration | FR-MIG-001..005 | P4 | 21 | Backlog | P4
EP-20 Migration | WCFM importer | US-MIG-002 | Import WCFM | - Field map | All | mercato-migration | FR-MIG-001..005 | P4 | 21 | Backlog | P4
EP-20 Migration | Mirakl CSV | US-MIG-003 | Import CSV | - Template | All | mercato-migration | FR-MIG-001..005 | P4 | 13 | Backlog | P4
EP-PLAT Observability | Tracing | US-PLAT-001 | OTel propagation | - W3C - Outbox - Kafka | - | mercato-core | NFR-Obs-006 | P1 MVP | 13 | Ready | P1
EP-PLAT Observability | SLO burn | US-PLAT-002 | Burn-rate alerts | - 1h/6h/1d | - | SRE | NFR-Obs-001 | P1 MVP | 8 | Ready | P1
EP-PLAT Security | CSP | US-PLAT-003 | CSP nonces | - SPA + storefront | - | Web | NFR-Sec-001 | P1 MVP | 8 | Ready | P1
EP-PLAT Security | MFA | US-PLAT-004 | MFA TOTP | - Recovery codes | - | mercato-core | NFR-Sec-002 | P1 MVP | 8 | Ready | P1
EP-PLAT Security | Audit | US-PLAT-005 | Audit log immutable | - Append-only - Object Lock | - | mercato-core | NFR-Sec-007 | P1 MVP | 13 | Ready | P1
EP-PLAT DR | Backups | US-PLAT-006 | PITR + snapshot copy | - Cross-account | - | SRE | NFR-DR-01..02 | P1 MVP | 8 | Ready | P1
EP-PLAT DR | DR drill | US-PLAT-007 | Monthly drill | - 1 random table - Replay | - | SRE | NFR-A-005..006 | P2 | 5 | Backlog | P2
EP-PLAT a11y | WCAG gate | US-PLAT-008 | axe-core in CI | - 0 violations | - | Web | NFR-Use-001 | P1 MVP | 8 | Ready | P1
EP-PLAT i18n | Locale catalog | US-PLAT-009 | ICU i18n | - 5 locales MVP | - | Web | NFR-I18n-01 | P2 | 13 | Backlog | P2
EP-PLAT Compliance | DSAR | US-PLAT-010 | DSAR automation | - 30d SLA | - | Compliance | §10.2 | P2 | 13 | Backlog | P2

## Epic Summary
Epic | Total Stories | MVP | P2 | P3 | P4 | Total Pts
EP-01 Core Framework | 7 | 7 | 0 | 0 | 0 | 52
EP-02 Vendor Lifecycle | 7 | 4 | 2 | 1 | 0 | 58
EP-03 Catalog | 8 | 3 | 5 | 0 | 0 | 83
EP-04 Orders | 6 | 5 | 1 | 0 | 0 | 63
EP-05 Commissions | 6 | 3 | 3 | 0 | 0 | 54
EP-06 Payouts | 6 | 5 | 1 | 0 | 0 | 60
EP-07 Reviews | 4 | 0 | 4 | 0 | 0 | 26
EP-08 Disputes | 4 | 0 | 4 | 0 | 0 | 36
EP-09 Messaging | 4 | 1 | 2 | 1 | 0 | 39
EP-10 Notifications | 4 | 1 | 3 | 0 | 0 | 34
EP-11 Reports | 3 | 0 | 3 | 0 | 0 | 26
EP-12 Search | 3 | 0 | 2 | 1 | 0 | 29
EP-13 Subscriptions | 2 | 0 | 0 | 2 | 0 | 29
EP-14 Tax | 2 | 0 | 1 | 1 | 0 | 18
EP-15 KYC | 3 | 2 | 1 | 0 | 0 | 26
EP-16 Fraud | 3 | 0 | 0 | 3 | 0 | 34
EP-17 AI | 6 | 0 | 0 | 6 | 0 | 73
EP-18 Collab | 2 | 0 | 0 | 0 | 2 | 21
EP-19 Enterprise | 5 | 3 | 0 | 2 | 0 | 63
EP-20 Migration | 3 | 0 | 0 | 0 | 3 | 55
EP-PLAT Compliance | 1 | 0 | 1 | 0 | 0 | 13
EP-PLAT DR | 2 | 1 | 1 | 0 | 0 | 13
EP-PLAT Observability | 2 | 2 | 0 | 0 | 0 | 21
EP-PLAT Security | 3 | 3 | 0 | 0 | 0 | 29
EP-PLAT a11y | 1 | 1 | 0 | 0 | 0 | 8
EP-PLAT i18n | 1 | 0 | 1 | 0 | 0 | 13
TOTAL | 98 | 41 | 35 | 17 | 5 | 976

## Phase Roadmap
Phase | Weeks | Story Count | Pts | Description
P1 MVP | week 0-12 | 41 | 395 | Core platform, vendor onboarding, multi-vendor checkout, commissions, weekly payouts, basic moderation.
P2 | week 12-22 | 35 | 304 | Reviews, disputes, reports, search, tax, bulk import, variations.
P3 | week 22-34 | 17 | 201 | Subscriptions, fraud, AI Copilot, collaboration, multi-currency, white-label.
P4 | week 34-44 | 5 | 76 | Migration importers, multi-region, BYOK, SSO, advanced AI.